## ActionItems
ACTION ITEM LIST
With PICK Ranking |  |  |  |  | Last Updated: | 2022-01-12 |  |  |  | PICK Chart
© 2017-2021 Vertex42 LLC
ACTION ITEMS | VALUE | DIFFICULTY | PICK | OWNER | ASSIGNED | DUE | STATUS | ✔ | NOTES
Task 0 | HIGH | EASY | I=Implement | JDI | 2022-01-02 | 2022-01-03 | 100% | ✔ |  | ► Task List Templates
Task 1 | LOW | EASY | P=Possible | Bill | 2022-01-02 | 2022-01-03 | 60% |  |  | ► More To Do Lists
Task 2 | HIGH | EASY | I=Implement | Sue | 2022-01-02 | 2022-01-10 | 30% |  |  | ► Project Management Templates
Task 3 | HIGH | HARD | C=Challenge | Bob | 2022-01-02 | 2022-01-11
Task 4 | LOW | HARD | K=Kill | Sally | 2022-01-02 | 2022-01-12

## Help
HELP |  | © 2017-2021 Vertex42.com
https://www.vertex42.com/ExcelTemplates/PICK-chart.html
About
This action item list template provides a simple way to list and track tasks assigned to different members of a group. It includes a PICK ranking based on choosing a low/high value and easy/hard difficulty.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn more about how to add drop-down lists and conditional formatting to your to do lists and action items lists, see the following blog post:
https://www.vertex42.com/blog/help/excel-help/add-cool-features-to-your-to-do-lists-in-excel.html
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.