## Schedule
CONSTRUCTION SCHEDULE |  |  |  |  | Construction Schedule Template © 2019 by Vertex42.com | [47 empty] | [42] | [6 empty] | [42]
ABC Construction, Inc.
Project Start: | 2019-05-01
Start Week: | 1
Today: | 2026-08-06 |  |  |  | 2019-04-29 | [6 empty] | 2019-05-06 | [6 empty] | 2019-05-13 | [6 empty] | 2019-05-20 | [6 empty] | 2019-05-27 | [6 empty] | 2019-06-03 | [6 empty] | 2019-06-10 | [6 empty] | 2019-06-17
 | time axis 2019-04-29 to 2019-06-23
TASK DESCRIPTION | START | END | LOAD | COLOR | time axis 2019-04-29 to 2019-06-23
|  |  |  | TOTAL DAILY LOAD: | 0 | 0 | 9 | 9 | 9 | 9 | 0 | 15 | 15 | 15 | 15 | 15 | 14 | 0 | 14 | 11 | 11 | 11 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase 1 Title | 2019-05-01 | 2019-05-21
Task 1 Description | 2019-05-01 | 2019-05-05 | 4 | B | 2019-05-01: 4; 2019-05-02: 4; 2019-05-03: 4; 2019-05-04: 4
Task 2 | 2019-05-06 | 2019-05-10 | 4 | G | 2019-05-06: 4; 2019-05-07: 4; 2019-05-08: 4; 2019-05-09: 4; 2019-05-10: 4
Task 3 | 2019-05-11 | 2019-05-13 | 3 | P | 2019-05-11: 3; 2019-05-13: 3
Phase 1 Milestone A | 2019-05-15 | 2019-05-15 |  | X
Task 4 | 2019-05-06 | 2019-05-09 | 6 | G | 2019-05-06: 6; 2019-05-07: 6; 2019-05-08: 6; 2019-05-09: 6
Task 5 | 2019-05-10 | 2019-05-17 | 6 | B | 2019-05-10: 6; 2019-05-11: 6; 2019-05-13: 6; 2019-05-14: 6; 2019-05-15: 6; 2019-05-16: 6; 2019-05-17: 6
Phase 1 Milestone B | 2019-05-21 | 2019-05-21 |  | X
Phase 2 Title
Task 1 | 2019-05-01 | 2019-05-03 | 5 | g | 2019-05-01: 5; 2019-05-02: 5; 2019-05-03: 5
Task 2 | 2019-05-04 | 2019-05-06 | 5 | g | 2019-05-04: 5; 2019-05-06: 5
Task 3 | 2019-05-07 | 2019-05-09 | 5 | g | 2019-05-07: 5; 2019-05-08: 5; 2019-05-09: 5
Task 4 | 2019-05-10 | 2019-05-12 | 5 | g | 2019-05-10: 5; 2019-05-11: 5
Task 5 | 2019-05-13 | 2019-05-15 | 5 | g | 2019-05-13: 5; 2019-05-14: 5; 2019-05-15: 5
Task 6 | 2019-05-16 | 2019-05-18 | 5 | g | 2019-05-16: 5; 2019-05-17: 5; 2019-05-18: 5
Insert new rows ABOVE this one
Construction Schedule Template © 2019 Vertex42.com
https://www.vertex42.com/ExcelTemplates/construction-schedule.html
Note on F9: TYPE: This column is set up to allow you to change the colors of the bar charts. Default (blank) = Gray B = Blue G = Green R = Red Y = Yellow O = Orange P = Purple X = Black

## NonWorkDays
Non-Work Days |  | Add dates to this list to highlight them in the gantt chart.
Date | Reason
1899-12-31 |  | ◄ Leave this row as-is. You can insert rows below it.
2019-05-27 | Memorial Day
2019-05-25 | Saturday before Memorial Day
2019-02-10 | Sunday
2019-02-17 | Sunday
2019-02-24 | Sunday
2019-03-03 | Sunday
2019-03-10 | Sunday
2019-03-17 | Sunday
2019-03-24 | Sunday
2019-03-31 | Sunday
2019-04-07 | Sunday
2019-04-14 | Sunday
2019-04-21 | Sunday
2019-04-28 | Sunday
2019-05-05 | Sunday
2019-05-12 | Sunday
2019-05-19 | Sunday
2019-05-26 | Sunday
2019-06-02 | Sunday
2019-06-09 | Sunday
2019-06-16 | Sunday
2019-06-23 | Sunday
2019-06-30 | Sunday
2019-07-07 | Sunday
2019-07-14 | Sunday
2019-07-21 | Sunday
2019-07-28 | Sunday
2019-08-04 | Sunday
2019-08-11 | Sunday

## Help
HELP
https://www.vertex42.com/ExcelTemplates/construction-schedule.html
© 2019 Vertex42 LLC
About
This construction schedule was designed to provide an extremely simple way to create a professional-looking construction schedule. The bars in the gantt chart are created automatically using conditional formatting. Other formatting is up to you.
Want more features?
Learn about Gantt Chart Template Pro
Work Load
This version of the construction schedule shows how you can display and sum work loads. For each task, you assign a numeric work load. This may represent number of workers or some other quantity that you want to use as a metric.
Every cell in the gantt chart area contains a formula that displays the work load for the task, and a row at the top of the chart sums each column to show the total load for that day.
Adding More Rows
When you insert new rows, you should insert a blank row between rows that have the formatting you want. If you do that, the formatting will be copied automatically.
IMPORTANT: After inserting a new row, copy a previous row and paste over the new row so that all of the formula are copied into the new row!
Listing Non Work Days
Instead of using the WORKDAY or WORKDAY.INTL functions, this construction schedule has you enter the nonworking days in a list in the NonWorkDays worksheet. This allows you to completely customize your work schedule.
Adding More Columns to the Gantt Chart
If you want to increase the time span shown in chart, you can copy the last column in the gantt chart and then paste the copied column to the right of the gantt chart.
Changing the Bar Colors
The TYPE column can be used to choose a color for the bars in the schedule. If you want to change how this columns works, you will need to edit the conditional formatting rules.
Conditional Formatting
If you want to edit the colors used in the gantt chart, you will need to edit the conditional formatting rules.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.

## ©
Daily Construction Schedule Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/construction-schedule.html
© 2019 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.