## SCurve
S-Curve Template | [6 empty] | #VALUE!
https://www.vertex42.com/lambda/scurve.html | [7 empty] | © 2024 Vertex42 LLC
Required: Microsoft 365
This worksheet uses a custom LAMBDA function, L_SCURVE, from the Vertex42 Lambda Library. The LAMBDA function requires Microsoft 365.
LAMBDA Functions Used in this File
doc | #VALUE! | L_SCURVE(startdates,enddates,values,[is_daily],[weekend],[holidays])
Instructions
Either update the table below with the dates and values that you want to include in your chart, or modify the L_SCURVE formulas to reference data from another worksheet. You can copy this worksheet into another workbook, but note that doing so will also copy the named functions and named ranges.
Project Tasks with Hours and Costs
Start Dates | End Dates | Daily Hours | Task Cost
2024-01-01 | 2024-01-05 | 8 | 1000
2024-01-06 | 2024-01-20 | 12 | 4500
2024-01-13 | 2024-01-27 | 20 | 7500
2024-01-20 | 2024-02-03 | 28 | 10500
2024-01-27 | 2024-02-10 | 20 | 7500
2024-02-03 | 2024-02-24 | 24 | 9000
2024-02-25 | 2024-03-03 | 20 | 4000
◄ Insert new rows above this one
weekend
0000011 | ◄ Entered as text, 0s or 1s, starting with Monday, so "0000011" means Saturday and Sunday are weekend days
holidays
1899-12-31 | ◄ Include at least one placeholder date like this one
2024-02-14
◄ Insert new rows above this one
Example Charts
Date | Daily Hours | Cumulative Hours |  | Date | Daily Cost | Cumulative Cost |  | Date | Daily Hours | % Complete
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
Formulas:
Start Dates = [End Dates, row above]+1
Start Dates = [Start Dates, row above]+7
End Dates = [Start Dates]+14

## ©
S-Curve Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/s-curve.html
© 2024 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet